## Sheet1
ASANTE AKIM CENTRAL MUNICIPAL ASSEMBLY
2020 COMPOSITE ANNUAL ACTION PLAN
No | Activity | Location | Source of Funds | Time Schedule |  |  |  | Budget (GH¢) | Implementing Agency
|  |  |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr |  | Lead | Collaborating
Goal 1:Build a Prosperous Society
1 | Implementation of one district one factory | Municipal Wide | DACF | X | X | X | X | 50000 | Agric | Central Administration
2 | Public Education on Revenue Mobilization | Municipal Wide | DACF | X | X | X | X | 300000 | Finance | Central Administration
3 | Street Naming | Municipal Wide | DACF | X | X | X |  | 80000 | PPD | Central Administration
4 | Completion of Pavalion at St. Mary and Wesley High School | Konongo | DACF | X |  |  |  | 100000 | GES | Works
5 | Public Health Education | Municipal Wide | DACF | X | X | X | X | 10000 | GHS/MEHO | Central Administration
Goal 2: Create Opportunities for All
No | Activity | Location | Source of Funds | Time Schedule |  |  |  | Budget (GH¢) | Implementing Agency
|  |  |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr |  | Lead | Collaborating
6 | Technology improvement training for women and farmers in income generating activities | Municipal Wide | DACF | X | X | X | X | 20000 | BAC | Central Administration
7 | Implementation of planting for Food and Jobs/Planting for export and Rural Development | Municipal Wide | DACF | X | X | X | X | 100000 | Agric | Central Administration
8 | Construction of 1 No 3 Unit Classroom Block, Ancilliary Facilities at Ohenenkwanta | Ohenenkwanta | DACF | X | X | X |  | 393000 | GES | Works
9 | Provision of Educational Furniture | Municipal Wide | DACF | X | X |  |  | 100000 | GES | Central Administration
10 | Construction of CHPs Compound at Annuruso Bye Water | Annuruso | DACF | X | X | X |  | 240000 | GHS | Central Administration
11 | Construction and Mechanisation of 4 No Boreholes | Konongo mrkt, Odumasi mrkt, Odumasi extension, Kyekyewere town centre | DDF |  | X | X | X | 151000 | Works | Central Administration
12 | Procure and supply PWD items to beneficiaries | Municipal Wide | DACF | X | X | X | X | 50000 | SW/CD | Central Administration
13 | Training of SMEs | Municipal Wide | DACF | X | X | X | X | 40000 | BAC | Central Administration
Goal 3:Safeguard the Natural Environment and Ensure a Resilient Built Environment
No | Activity | Location | Source of Funds | Time Schedule |  |  |  | Budget (GH¢) | Implementing Agency
|  |  |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr |  | Lead | Collaborating
14 | Rehabilitation of Roads in the Municipality | Municipal Wide | DACF | X | X | X |  | 100000 | Road | Central Administration
15 | Roll back Malaria Control Programme | Municipal Wide | DACF | X | X | X |  | 4106360 | GHS/MEHO | Central Administration
16 | Commerate World AIDS Day for counselling and testing | Municipal Wide | DACF | X | X | X | X | 4106360 | GHS/MEHO | Central Administration
17 | Training of PWDs in basic book and record keeping | Municipal Wide | DACF | X | X | X | X | 40000 | BAC | Central Administration
18 | Evacuation of refuse dump and dislodging of liquid waste to final disposal site | Municipal Wide | DACF | X | X | X | X | 41000 | MEHO | Central Administration
19 | Fumigation/Disinfection | Municipal Wide | DACF | X | X | X | X | 184000 | GHS/MEHO | Central Administration
20 | Environmental Health Inspection (schools & houses) | Municipal Wide | DACF | X | X | X | X | 230000 | MEHO | Central Administration
21 | Registration of businesses | Municipal Wide | DACF | X | X | X | X | 40000 | BAC | Central Administration
22 | Tree planting | Municipal Wide | DACF |  |  | X | X | 40000 | Agric | Central Administration
23 | Sensitization of drivers on road safety | Municipal Wide | DACF | X | X | X | X | 20000 | Central Administration | Transport
24 | Drilling and mechanization of 6 No. boreholes | Bimma, Dwease, Adumkrom, Obenimase, Patriensa, Odumasi extension | I.G.F | X | X | X | X | 239274 | Works | Central Administration
25 | Construction of 3 No. 10 seater squat W/C toilet with mechanized borehole | Agyareago, Kramokrom, Praaso | DDF | X | X | X | X | 558000 | Works | Central Administration
26 | Registration of public transport operators, vehicles, drivers and terminals | Municipal Wide | DACF | X | X | X | X | 5000 | Central Administration | Transport
27 | Public education on road safety in selected communities | Municipal Wide | DACF | X | X | X | X | 15000 | Central Administration | Transport
28 | Construction of 1 No. 1/900MM Pipe Culvert with Approach Fill | Wiamokrom | MP Common Fund | X | X |  |  | 16000 | Works | Central Administration
29 | Public education on bushfire prevention | Municipal Wide | DACF | X | X | X | X | 20000 | MEHO | Central Administration
30 | Construction of 1 No. 11 Unit Market Shed with Urinal at Kyekyebiase | Kyekyebiase | DACF | X | X | X | X | 88041 | Works | Central Administration
31 | Desilting of choked drains | Municipal Wide | DACF | X | X | X | X | 20000 | MEHO | Central Administration
32 | Food screening | Municipal Wide | DACF | X | X | X | X | 30000 | MEHO | Central Administration
33 | Procurement of 1 No Motorbike for Environmental Health Unit | Konongo- Odumasi | DACF | X | X |  |  | 5000 | GHS | Central Administration
Goal 4: Maintain a stable, united and safe society
No | Activity | Location | Source of Funds | Time Schedule |  |  |  | Budget (GH¢) | Implementing Agency
|  |  |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr |  | Lead | Collaborating
34 | Procurement of Electricity Poles and Accessories | Municipal Wide | DACF | X | X |  |  | 150000 | Works | Central Administration
35 | Procure and supply roofing sheets and cement for Community Self Help Projects | Municipal Wide | DACF | X | X | X | X | 20531801 | Central Administration | Works
36 | Disaster Relief and Management | Municipal Wide | DACF | X | X | X | X | 100000 | NADMO | Central Administration
37 | Procure and supply streetlights and accessories to the three zonal council | Municipal Wide | DACF | X | X | X | X | 8212720 | Central Administration
38 | Public Fora | Municipal Wide | DACF | X | X | X | X | 100000 | Central Administration
39 | Provide temporal structure for security services | Municipal Wide | DACF | X | X | X | X | 30000 | Central Administration
40 | Procurement/Maintenance of Office Machines/Computers | Municipal Wide | DACF | X | X | X | X | 40000 | Central Administration
41 | Procurement/Maintenance of Office Furniture/Assembly hall | Municipal Wide | DACF | X | X | X | X | 50000 | Central Administration
42 | Project Management/ Monitoring of projects and support to MPCU | Municipal Wide | DACF | X | X | X | X | 40000 | Central Administration
43 | Revision of Medium Term dev't Plan and Composite Budget | Konongo | DACF | X | X | X | X | 40000 | Central Administration
44 | National Day Celebrations (Farmers Day, 6th March and 1st July) | Municipal Wide | DACF | X | X | X | X | 150000 | Central Administration | Agric/ GHS/GES/GPS
45 | Renovation of Assembly Properties | Konongo | DACF | X | X | X |  | 275000 | Works | Central Administration
46 | Release of Funds to Decentralized Department | Municipal Wide | DACF | X | X | X | X | 82500 | Central Administration | Finance
47 | Construction of Ambulance Unit | Konongo- Odumasi | DDF | X | X | X |  | 601499.34 | Works | GHS
48 | Capacity Building | Municipal Wide | DDF | X | X | X | X | 34615.38 | HR | Central Administration
49 | construction 1No. 5 Unit KG and lower primary classroom block with ancillary facility, 5 seater squat w/c toilet with mechaized bore and over tank and supply of school furniture | kyekyewere | DDF | X | X | X | X | 436122 | Works | Central Administration