## 2021 AAP
ASANTE AKIM CENTRAL MUNICIPAL ASSEMBLY
2021 COMPOSITE ANNUAL ACTION PLAN
No | Activity | Location | Source of Funds | Time Schedule |  |  |  | Budget (GH¢) | Implementing Agency
|  |  |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr |  | Lead | Collaborating
Goal 1:Build a Prosperous Society
1 | Implementation of one district one factory | Municipal Wide | DACF | X | X | X | X | 100000 | Agric | Central Administration
2 | Public Education on Revenue Mobilization | Municipal Wide | DACF | X | X | X | X | 30000 | Finance | Central Administration
3 | Valuation of Properties | Municipal Wide | DACF | X | X | X | X | 100000 | Finance | Central Administration
4 | Street Naming | Municipal Wide | DACF | X | X | X |  | 80000 | PPD | Central Administration
5 | Public Health Education | Municipal Wide | DACF | X | X | X | X | 10000 | GHS/MEHO | Central Administration
Goal 2: Create Opportunities for All
No | Activity | Location | Source of Funds | Time Schedule |  |  |  | Budget (GH¢) | Implementing Agency
|  |  |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr |  | Lead | Collaborating
6 | Technnology improvement training for income generatiing groups and businesses | Municipal Wide | DACF | X | X | X | X | 20000 | BAC | Central Administration
7 | Implementation of planting for Food and Jobs/Planting for export and Rural Development | Municipal Wide | DACF | X | X | X | X | 100000 | Agric | Central Administration
8 | Construction of 1 No 3 Unit Classroom Block, Ancilliary Facilities at Ohenenkwanta | Ohenenkwanta | DACF | X | X | X |  | 326349.7 | Works | GES
9 | Construction of 3 Unit Classroom Block with ancillary Facilities | Nsiakrom | DACF | X | X | X |  | 400000 | Works | GES
10 | Completion of 1 No. 5 Unit Classroom Block | Kyekyewere | DDF | x | x | x |  | 279303.5 | GES | Works
11 | Construction of 1 No. CHPs Compound with chamber and hall quarters at By Water | Konongo | DACF | X | X | X | X | 350000 | GHS | Central Administration
12 | Municipal Education Fund for scholarships and bursary | Municipal Wide | DACF | X | X | X | X | 82127.2 | Central Administration | GES
13 | BECE mock exams and STMIE activities | Municipal Wide | DACF | X | X | X | X | 50000 | Central Administration | GES
14 | Provision of Educational Furniture | Municipal Wide | DACF | X | X |  |  | 100000 | Central Administration | GES
15 | Construction of CHPs Compound at Annuruso | Annuruso | DACF | X | X | X |  | 350000 | GHS | Central Administration
16 | Construction of 1 No. CHPs Compound | Nsiakrom | DDF | X | X | X | X | 310000 | Central Administration | GHS
17 | Construction and Mechanisation of 4 No Borehole | Municipal Wide | DACF | X | X | X |  | 200000 | Works | Central Administration/ GES
18 | Construction and Mechanisation of 5 No Borehole | Anhwereso, Anuruso, Ohene Nkwanta, Beposo, Patriensa Kwaem | IGF | X | X | X |  | 200000 | Works | Central Administration
19 | Training alternative livelihood for farmers and food processing groups | Municipal Wide | DACF | X | X | X | X | 40000 | Central Administration
Goal 3:Safeguard the Natural Environment and Ensure a Resilient Built Environment
No | Activity | Location | Source of Funds | Time Schedule |  |  |  | Budget (GH¢) | Implementing Agency
|  |  |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr |  | Lead | Collaborating
20 | Rehabilitation of Roads in the Municipality | Municipal Wide | DACF | X | X | X |  | 100000 | Works | Central Administration
21 | Roll back Malaria Control Programme | Municipal Wide | DACF | X | X | X |  | 20531.8 | GHS/MEHO | Central Administration
22 | Mark World AIDS Day for condom distribution and testing | Municipal Wide | DACF | X | X | X | X | 20531.8 | GHS/MEHO | Central Administration
23 | Evacuation of refuse dump to final disposal site | Municipal Wide | DACF | X | X | X | X | 46000 | MEHO | Central Administration
24 | Fumigation | Municipal Wide | DACF | X | X | X | X | 307191 | GHS/MEHO | Central Administration
25 | Sanitation Improvement (cleaning of public places) | Municipal Wide | DACF | X | X | X | X | 230000 | MEHO | Central Administration
26 | Dislodging of Liquid waste to final disposal site | Municipal Wide | DACF | X | X | X | X | 30000 | MEHO | Central Administration
27 | Construction of toilet facilities | Dwease | DACF | X | X | X | X | 244000 | GHS | Central Administration
28 | Construction of 1 No. 10 seater public toilet facilities | Agyareago | DDF | X | X | X | X | 199630 | Central Administration | GHS
Goal 4: Maintain a stable, united and safe society
No | Activity | Location | Source of Funds | Time Schedule |  |  |  | Budget (GH¢) | Implementing Agency
|  |  |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr |  | Lead | Collaborating
29 | Procurement of Electricity Poles and Accessories | Municipal Wide | DACF | X | X |  |  | 100000 | Works | Central Administration
30 | Maintenance of Market | Municipal Wide | DACF |  | X | X |  | 100000 | Works | Central Administration
31 | Maintenance of 10 no. boreholes and Water Improvement system in the Municipality | Municipal Wide | DACF | X | X | X | X | 70000 | Works | Central Administration
32 | Procure and supply roofing sheets and cement for Community Self Help Projects | Municipal Wide | DACF | X | X | X | X | 205318.01 | Central Administration | Works
33 | Disaster Relief and Management | Municipal Wide | DACF | X | X | X | X | 100000 | NADMO | Central Administration
34 | Procure streetlights, bulbs and accessories for zonal council | Municipal Wide | DACF | X | X | X | X | 82127.2 | Central Administration
35 | Public Fora | Municipal Wide | DACF | X | X | X | X | 100000 | Central Administration
36 | Monthly and quarterly MUSEC meetings | Municipal Wide | DACF | X | X | X | X | 30000 | Central Administration | GPS
37 | Procurement/Maintenance of Office Machines/Computers | Municipal Wide | DACF | X | X | X | X | 40000 | Central Administration
38 | Procurement/Maintenance of Office Furniture/Assembly hall | Municipal Wide | DACF | X | X | X | X | 50000 | Central Administration
39 | Data Collection for Project Management/ Monitoring of projects and support to MPCU | Municipal Wide | DACF | X | X | X | X | 40000 | Central Administration
40 | Revision of Medium Term dev't Plan and Composite Budget | Konongo | DACF | X | X | X | X | 40000 | Central Administration
41 | National Day Celebrations (Farmers Day, 6th March and 1st July) | Municipal Wide | DACF | X | X | X | X | 150000 | Central Administration | Agric/ GHS/GES/GPS
42 | Renovation of 10 No. Low cost staff bungalow | Konongo | DACF | X | X | X | X | 100000 | Works | Central Administration
43 | Release of Funds to Decentralized Department | Municipal Wide | DACF | X | X | X | X | 115000 | Central Administration | Finance
44 | Construction of Ambulance Unit | Konongo- Odumasi | DDF | X | X | X | X | 182586.96 | Central Administration | GHS
45 | Capacity Building | Municipal Wide | DDF | X | X | X | X | 100000 | Central Administration | HR
46 | Construction of 1 No. 10 seater public toilet facilities | Praaso | DDF | X | X | X | X | 199630 | Central Administration | GHS
47 | Construction of 1 No. 10 seater public toilet facilities | Kramokrom | DDF | X | X | X | X | 199630 | Central Administration | GHS
48 | Construction of 1 No. 10 seater public toilet facilities | Anuruso | DACF | X | X | X | X | 250000 | Central Administration | GHS
49 | Construction of 2 No. 6 Unit Classroom Block | KOSS Model | DACF | x | x | x |  | 1200000 | GES | Works
50 | LEAP Programme | Mun. wide | DACF | x | x | x | x | 50000 | Social welfare | Central Admin
51 | Procure and supply PWD items to beneficiaries | Mun. wide | DACF | X | X | X | X | 350000 | Social welfare | Central Admin