## 2023 AAP
ASANTE AKIM CENTRAL MUNICIPAL ASSEMBLY
2023 COMPOSITE ANNUAL ACTION PLAN
No | Activity | Location | Source of Funds | Time Schedule |  |  |  | Budget (GH¢) | Implementing Agency
|  |  |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr |  | Lead | Collaborating
ECONOMIC
1 | Acquisition of 1 no. 50KVA mounted transformer for cassava factory | Municipal Wide | DACF | X | X |  |  | 60000 | Works | Central Administration
2 | Construction of 1No. 11 unit Market shed with Urinal | Kyekyebiase | DACF | X | X | X | X | 45645.6 | Works | Central Administration
3 | Support the implementation of MAG activities/ planting for food and jobs/planting for export and Rural development phase II | Municipal Wide | DACF | X | X | X | X | 20000 | Agric | Central Administration
SOCIAL DEVELOPMENT
No | Activity | Location | Source of Funds | Time Schedule |  |  |  | Budget (GH¢) | Implementing Agency
|  |  |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr |  | Lead | Collaborating
4 | Construction of 1 No 3 Unit Classroom Block, Ancilliary Facilities | Ohenenkwanta | DACF | X | X |  |  | 111203.53 | GES | Works
5 | Provision of Educational Furniture | Municipal Wide | DACF | X | X | X | X | 300000 | GES | Works
6 | Organise outreach programme on malaria prevention and control | Municipal Wide | DACF | X | X | X | X | 7000 | GHS | Central Administration
7 | Implement the activities of Municipal AIDS committee | Municipal Wide | DACF | X | X | X | X | 14000 | GHS | Central Administration
8 | Organise public Health Education on Environmental sanitation and Hygiene. | Municipal Wide | DACF | X | X | X | X | 3500 | GHS | Central Administration
9 | Organise Local Training Programme for SMEs | Municipal Wide | DACF | X | X | X | X | 100000 | BAC | AGRIC
10 | Construction of 1 No. CHPS Compound at Nsiakrom | Nsiakrom | DACF/RFG | X | X | X | X | 200323.82 | Works | Central Administration
11 | Construction of 1 No. 3 Unit classroom block with office, store and staff common room | Dwease | DACF/RFG | X | X | X | X | 400000 | Works | Central Administration
12 | Construction of 1 No. 1storey 6 Unit classroom block with office, store and staff common room | Odumasi Presby | DACF/RFG | X | X | X | X | 800000 | Works | Central Administration
13 | Construction of 1No. 3-Unit Classroom Block with Ancillary Facilities at KOSS Model School | KOSS Model School | DACF/RFG | X | X | X | X | 400000 | Works | Central Administration
14 | Renovation of MCD, Asst Dir and Asst Eng Bungalow | Konongo Lowcost | DACF | X | X | X | X | 199925.8 | Works | Central Administration
15 | Renovation of Planning, Budget and Finance Officer’s Bungalow | Konongo Extension | DACF | X | X | X | X | 199994.3 | Works | Central Administration
16 | Renovation of Procurement Officer’s Bungalow | Konongo Extension | DACF | X | X | X | X | 168497 | Works | Central Administration
17 | Rehabilitation of the Official Residence of Mun. Director of Agriculture | Konongo Extension | DACF | X | X | X | X | 393230 | Works | Central Administration
ENVIRONMENT INFRASTRUCTURE AND HUMAN SETTLEMENTS
No | Activity | Location | Source of Funds | Time Schedule |  |  |  | Budget (GH¢) | Implementing Agency
|  |  |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr |  | Lead | Collaborating
18 | Procurement of Electricity Poles and Accessories | Municipal wide | DACF | X | X | X | X | 200000 | Works | Central Administration
19 | Rehabiliation of Roads (20km) | Odumasi Junction-Agyareago, Tripple Lane, Odumasi Santeneso | Road Fund | X | X | X | X | 350000 | Road | Central Administration
20 | Organise quaterly Anti-fire campaigns | Municipal wide | DACF | X | X | X | x | 5950 | NADMO | Central Administration
21 | Undertake quarterly monitoring of small scale mining sites to ensure compliance with mining regulations | Municipal wide | DACF | x | x | x | x | 5404 | NADMO | Central Administration
22 | Conduct monthly Hazard mapping of the Municipality | Municipal wide | DACF | x | x | x |  | 5000 | NADMO | Central Administration
23 | Evacuation and levelling of refuse dumps | Municipal Wide | DACF | X | X | X | X | 100000 | MEHO | Central Administration
24 | Fumigation exercise to disinfect sanitary sites. | Municipal Wide | DACF | X | X | X | X | 307191 | MEHO | Central Administration
25 | Underatake clean up exercises and desilting of choked gutters at Central Business District and surrounding communities | Municipal Wide | DACF | X | X | X | X | 230000 | MEHO | Central Administration
26 | Organise Community Mobilizatiuon and Education Programme on Child rights and protections | Municipal wide | DACF | X | X | X | X | 5400 | Social Welfare
27 | Community mobilization and education on child rights and parents responsibilities | Municipal wide | DACF | X | X | X | X | 5000 | Social Welfare
28 | Public Education on Noise pollution and Air Quality Control | Municipal Wide | DACF | X | X | X | X | 5000 | MEHO | Central Administration
29 | Celebrationn of Maiden Asante Akim Central August Festival (AACAFEST) to promote tourism in the Municipality | Municipal Wide | DACF | X | X | X | X | 100000 | Central Administration | stakeholders
30 | Dislodge and dispose liquid waste to final disposal site at Bomireso | Municipal Wide | DACF | X | X | X | X | 30000 | MEHO | Central Administration
GOVERNANCE, CORRUPTION AND PUBLIC ACCOUNTABILITY
No | Activity | Location | Source of Funds | Time Schedule |  |  |  | Budget (GH¢) | Implementing Agency
|  |  |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr |  | Lead | Collaborating
31 | Public Education on Revenue Mobilization | Municipal Wide | DACF | X | X | X | X | 8000 | Finance | Central Administration
32 | Street Naming | Municipal Wide | DACF | X | X | X | X | 20000 | PPD | Central Administration
33 | Support to Sub Municipal Structures (2%) | Municipal Wide | DACF | X | X | X | X | 11050 | Central Administration
34 | Organise Public fora/town hall meetings on Government policies and interventions | Municipal Wide | DACF | X | X | X | X | 45000 | Central Administration
35 | Organise quarterly and emergency Municpal Security Committee meetings (MUSEC) | Municipal Wide | DACF | X | X | X | X | 30000 | Central Administration
36 | Procurement/Maintenance of Office Machines/Computers/Furniture | Municipal Wide | DACF | X | X | X | X | 200000 | Central Administration
37 | Procurement of stationaries | Municipal Wide | DACF | X | X | X | X | 50000 | Central Administration
38 | Maintenance and repairs of Official vehicles | Municipal Wide | DACF | X | X | X | X | 45000 | Central Administration
39 | Project Management/Monitoring of projects and support to MPCU | Municipal Wide | DACF | X | X | X | X | 50000 | Central Administration
40 | Preparation of Medium Term dev't Plan and Preparation of Composite Budget (Stakeholders engagement/Meetings etc) | Konongo | DACF | X | X | X | X | 60000 | Central Administration
41 | Support to Departments | Konongo | DACF | X | X | X | X | 28030 | Central Administration
42 | Operation and Maintenance (Assembly Office and Buildings) | Konongo-Odumasi | DACF | X | X | X | X | 77169.85 | Works | Central Administration
43 | Organise capacity building programmes for staff of the Assembly | mun wide | DACF-RFG | X | X | X | X | 45000 | HR | Central Administration

## AGRIC
ASANTE AKIM CENTRAL MUNICIPAL ASSEMBLY
2022 COMPOSITE ANNUAL ACTION PLAN
No | Activity | Location | Source of Funds | Time Schedule |  |  |  | Budget (GH¢) | Implementing Agency
|  |  |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr |  | Lead | Collaborating
0
1 | Implementation of one district one factory | Municipal Wide | DACF | X | X | X | X | 10000 | Agric | Central Administration
2 | Implementation of planting for food and jobs/planting for export and Rural development | Municipal Wide | DACF | X | X | X | X | 20000 | Agric | Central Administration