## Sheet1
ASANTE AKIM CENTRAL MUNICIPAL ASSEMBLY
2022 COMPOSITE ANNUAL ACTION PLAN
No | Activity | Location | Source of Funds | Time Schedule |  |  |  | Budget (GH¢) | Implementing Agency
|  |  |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr |  | Lead | Collaborating
0
1 | Implementation of one district one factory | Municipal Wide | DACF | X | X | X | X | 50000 | Agric | Central Administration
2 | Acquisition of 1 no. 50KVA mounted transformer for cassava factory | Municipal Wide | DACF | X | X |  |  | 80000 | Works | Central Administration
3 | Registration and formalization of business enterprises with Registrar General Department | Municipal Wide | DACF | X | X |  |  | 5000 | BAC | Central Administration
4 | Construction of 1no 11 unit Market shed with Urinal | Kyekyebiase | DACF | X | X | X | X | 88041 | Works | Central Administration
5 | Organise education and training to empower women groups on income generating activities | Obenimase | DACF | X | X | X | X | 7500 | Social Welfare | BAC
6 | Implementation of planting for food and jobs/planting for export and Rural development | Municipal Wide | DACF | X | X | X | X | 50000 | Agric | Central Administration
SOCIAL DEVELOPMENT
No | Activity | Location | Source of Funds | Time Schedule |  |  |  | Budget (GH¢) | Implementing Agency
|  |  |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr |  | Lead | Collaborating
7 | Construction of 1 No 3 Unit Classroom Block, Ancilliary Facilities | Ohenenkwanta | DACF | X | X |  |  | 111203.53 | GES | Works
8 | Distribution of Items to PWDs | Municipal wide | DACF | X | X | X | X | 12250 | Social Welfare
9 | Provision of Educational Furniture | Municipal Wide | DACF | X | X | X | X | 100000 | GES | Works
10 | 0rganise outreach prgramme on malaria prevention and control and distribution of mosquitoes nets to pregnant women | Municipal Wide | DACF | X | X | X | X | 26476.2 | GHS | Central Administration
11 | Implementation of LEAP programme | mun wide | DACF | X | X | X | X | 4680 | Social Welfare
12 | Implementation the activities of Municipal AIDS Committee. | Municipal Wide | DACF | X | X | X | X | 26044,98 | GHS | Central Administration
13 | Training of three (3) women groups on cockerel production | Dwease, Kyekyebiase and Obenimase | DACF | X | X | X | X | 5000 | Agric | Central Administration
14 | Organise public health education on food hygiene and evironmental sanitation | Municipal Wide | DACF | X | X | X | X | 10000 | GHS | Central Administration
15 | Organise public education on menstrual hygiene and distribution of 500 sanitary pads to females pupils at Agyareago M/A | mun wide | DACF | X | X | X | X | 10000 | Social Welfare | Health
16 | Train women on the nutritional benefits of unpolished rice to promote local businesses | Municipal Wide | DACF | X | X | X | X | 5190 | Agric | BAC
17 | Construction of 1 no. CHPS Compound at Nsiakrom | Nsiakrom | DACF/RFG | X | X | X | X | 517000 | Works | Central Administration
18 | Drilling and mechanisation of 4 no. borehole | odumasi market, konongo market, Konongo lorry station, kyekyewere town centre | DACF/RFG | X | X |  |  | 52010.4 | Works | Central Administration
19 | Sensitization on Gender Based Violence | Dwease, Kyekyebiase and Odumasi | DACF | X | X | X | X | 6365 | Social Welfare
20 | Drilling and mechanization of 6 No. boreholes | Bimma, Dwease, Kramokrom, Obenimase, Patriensa, Odumasi extension | IGF | X | X |  |  | 81930.02 | Works | Central Administration
21 | Construction of 1No. 1-Storey 6-Unit Classroom block with Office, Store, Staff Common room and Library for Odumasi Presby Primary school | Odumasi Presby Primary school | DACF-RFG |  |  |  | X | 798898 | GES | Works
22 | Construction of 1No. 3-Unit Classroom block with Office, Store, Staff Common room at Dwease primary school | Dwease primary school | DACF-RFG |  |  |  | X | 399063 | GES | Works
ENVIRONMENT INFRASTRUCTURE AND HUMAN SETTLEMENTS
No | Activity | Location | Source of Funds | Time Schedule |  |  |  | Budget (GH¢) | Implementing Agency
|  |  |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr |  | Lead | Collaborating
23 | Procurement of Electricity Poles and Accessories | Municipal wide | DACF | X | X | X | X | 200000 | Works | Central Administration
24 | Reshaping and sectional gravel of KOSS Junction to Konongo Zongo Junction Road (1.8KM) | Municipal wide | DACF | X | X | X | X | 65000 | Road | Central Administration
25 | Green Ghana Day- Tree Planting Exercise | mun wide | DACF | X | X | X | X | 20000 | Agric | Central Administration
26 | Disaster Prevention and Management | Municipal wide | DACF | X | X | X | X | 100000 | NADMO | Central Administration
27 | Evacuation and levelling of refuse dumps | Municipal Wide | DACF | X | X | X | X | 46000 | MEHO | Central Administration
28 | Organise sensitization programme for farmers on bushfire prevention, mitgation and awareness raising. | mun wide | DACF | X | X | X | X | 14970 | Agric | NADMO
29 | Fumigation exercise to disinfect sanitary sites | Municipal Wide | DACF | X | X | X | X | 307191 | MEHO | Central Administration
30 | Organise clean-up exercise and disilting of choked gutters at the Central Business District surrounding communities | Municipal Wide | DACF | X | X | X | X | 230000 | MEHO | Central Administration
31 | Dislodge and dispose liquid wastes to final disposal sites at Bomireso | Municipal Wide | DACF | X | X | X | X | 30000 | MEHO | Central Administration
GOVERNANCE, CORRUPTION AND PUBLIC ACCOUNTABILITY
No | Activity | Location | Source of Funds | Time Schedule |  |  |  | Budget (GH¢) | Implementing Agency
|  |  |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr |  | Lead | Collaborating
32 | Public Education on Revenue Mobilization | Municipal Wide | DACF | X | X | X | X | 60000 | Finance | Central Administration
33 | Street Naming | Municipal Wide | DACF | X | X | X | X | 20000 | PPD | Central Administration
34 | Support to Sub Municipal Sub Structures (2%) | Municipal Wide | DACF | X | X | X | X | 104179.9 | Central Administration
35 | Organise public fora /town hall meetings on government policies and internentions | Municipal Wide | DACF | X | X | X | X | 200000 | Central Administration
36 | Organise quarterly and emergency Municipal Security Committee (MUSEC) meetings | Municipal Wide | DACF | X | X | X | X | 30000 | Central Administration
37 | Procurement/Maintenance of Office Machines/Computers/Furniture/Stationery | Municipal Wide | DACF | X | X | X | X | 100000 | Central Administration
38 | Project Management/ Monitoring of projects and support to MPCU | Municipal Wide | DACF | X | X | X | X | 40000 | Central Administration
39 | Preparation of Medium Term dev't Plan and Preparation of Composite Budget (Stakeholders engagement/Meetings etc) | Konongo | DACF | X | X | X | X | 100000 | Central Administration
40 | Support to Departments | Konongo | DACF | X | X | X | X | 120000 | Central Administration
41 | Sensitize pupils of Odumasi Anglican and Presby School on zebra crossing | mun wide | DACF | X | X | X | X | 20000 | Transport | Central Administration
42 | National Day Celebrations (Farmers Day, 6th March and 1st July) | Municipal Wide | DACF | X | X | X | X | 150000 | Central Administration
43 | Operation and Maintenance (Assembly Office and Buildings) | Konongo-Odumasi | DACF | X | X | X | X | 1046224.54 | Works | Central Administration
44 | Capacity building for staff of the Assembly | mun wide | DACF-RFG | X | X | X | X | 45859 | HR | Central Administration
45 | Rehabilitation of the residence of the Municipal Chief Executive | Konongo-Lowcost | DACF | X |  |  |  | 125137 | Works | Central Administration
46 | Registration and orientation of Transport Operators on Road Safety | mun wide | DACF | X | X | X | X | 25000 | Transport | Central Administration
47 | Renovation of Main Municipal Administration Block Phase II | Konongo-Odumasi | DACF | X | X | X | X | 19327.9 | Central Administration