ASANTE AKIM CENTRAL MUNICIPAL ASSEMBLY

2019 ANNUAL PROGRESS REPORT

MUNICIPAL PLANNING CO-ORDINATING UNIT

JANUARY, 2020

# EXECUTIVE SUMMARY

The 2019 Annual Progress Reports catalogues the achievements and challenges of the Municipal in the implementation of the Annual Action Plan of the Municipal Medium Term Development Plan, 2018-2021, of the Asante Akim Central Assembly.

The report has been organized into three chapters. The opening chapter outlines mainly the purpose for the preparation of the APR, the activities involved and the stakeholders. The second chapter delves into the M&E activities for the period. It provides the proposed activities and how far they have been achieved within the year. It also provides the revenue and expenditure performance for the year. The revenue Table showed a continual meagre internally generated revenue as compared to the Grants. Lands and concessions and Fees and Fines continue to be the revenue items that provide internally generated revenue of the Assembly.

Performance indicators of development for the District and the National level has been provided but there is not enough data for all the indicators. The district level statistics have been stated but the challenges exist especially for the sex disaggregation of the data.

Other critical areas for which information was readily available were presented in the last chapter. Issues of education, Social Protection Programmes, skills development and agriculture. Issues of gender inequity, road infrastructure, environmental and climate change issues, HIV/AIDS have been duly presented. Some of the challenges of the entire process of reporting and the recommendations have been suggested to conclude the report.

# CHAPTER ONE

# GENERAL INTRODUCTION

## 1.1 Introduction

The report covers the period from 1st January to 31st December 2019. It covers the programmes and project activities carried out based on the planned programmes and projects of the Assembly. It also collates, harmonizes and reports on the activities, achievements and challenges of the various decentralized Departments and Agencies in the Municipality in their bid to implement activities set out in the 2018-2021 MTDP. The report is prepared in line with the DEVELOPMENT DIMENSIONS outlined under Agenda for Jobs listed below

- Economic Development

- Social Development

- Environment Infrastructure and Human Settlements

- Governance Corruption and Public Accountability.

This is the second in the series of annual reports prepared to monitor the implementation of the 2018-2021 Municipal Medium Term Development Plan. In a bid to measure progress, the Municipal Planning Coordinating Unit ((MPCU) prepared a Monitoring and Evaluation (M&E) plan to guide the implementation of the MMTDP 2018 – 2021. The report therefore is to measure the extent to which the indicators set in the M&E plan is being achieved for the year 2019.

## 1.2 Purpose of M&E for 2019

The purpose of the 2019 M&E report is to assess or evaluate the performance of the Asante Akim Central Municipal Assembly, review and provide information on the achievements and impacts of the Assembly based on the objectives set out in the MTDP, Monitoring and Evaluation Plan, Programmes and Projects targeted in the Annual Action Plan (2019). It also highlights the constraints and challenges faced in the implementation, monitoring and evaluation of the activities and make recommendations thereon.

The report also contains the performance indicators of the various sectors of the municipal economy, the challenges and lessons learnt, and the way forward towards achieving the development agenda as laid out in the MTDP.

1.3 Summary of achievement of the implementation of Municipal MTDP (2018-2021)

1.3.1 Brief profile of the Municipality

The Asante Akim Central Municipal Assembly is one of the thirty (34) MMDAs in the Ashanti Region. It was created by L.I 2056 and it has Konongo-Odumasi as its twin Capital Town. It was carved out of the then Asante Akim District Council in 1988 and was elevated to Municipality status by legislative Instrument 1907 in November 2007. Until July 2012 it used to be Asante Akim North Municipal Assembly but with the carving out of Asante Akim North District Assembly, the name was changed to Asante Akim Central Municipal Assembly. For the purpose of decentralization and local government representation, the Municipality has one (1) electoral constituency for parliamentary representation, Twenty-five (25) electoral areas for Municipal Assembly representation and three Zonal Councils namely;

- Konongo-Odumasi

- Owereagya

- Dwease-Praaso

The Municipality is located in the Eastern part of the Ashanti Region. The Municipality shares boundaries with Asante Akim North at the North, Ejisu-Juaben and Sekyere East at the West, Asante Akim South at the East and South and Bosome- Freho District at the South – West.

1.3.2 Vision

The Asante Akim Central Municipal Assembly aspires to become a safe and peaceful municipality of prosperous people with excellent infrastructure and services delivered by a peak performing Assembly in partnership with stakeholders.

1.3.3	Mission

The Asante Akim Central Municipal Assembly exists to ensure a better standard of living by providing the right leadership in the development of infrastructure and delivery of socio-economic services through stakeholder participation with equal opportunities for all.

1.3.4	Core Values

The Assembly’s core values and principles guide every aspect of its business from the people we hire, to our products and services, to our business partners and customers. The five core values comprise:

- Respect for each other

- Hard work and High performance

- Opportunity for all; care for the vulnerable

- Transparency and Accountability

To achieve this mission and vision the Assembly has set the following objectives

- To improve the quality of life of the people through sustainable development.

- To facilitate the effective functioning of the local government institutions in the Municipality

- To ensure efficiency and effectiveness in the mobilization and utilization of resources in the Municipality by the Assembly and its decentralized departments

- To monitor, co-ordinate and harmonize the implementation of development plans and activities in the Municipality

- To facilitate the provision of basic social and economic infrastructure and services in the municipality

- To facilitate community-based and private sector development in private sector in the Municipality.

## 1.4 Challenges encountered in the Implementation of the MMTDP

Developing any report usually comes with diverse challenges.

The following are some of the challenges faced by the MPCU during the preparation of this annual progress report.

- Inadequate logistics for the MPCU activities

- Untimely submission of Departmental report.

- Difficulty in getting data from non-decentralize agency and organization especially on central government intervention such as IPEP, School Feeding Program, One Million One Constituency etc.

1.5 Processes involved

The process for the preparation of the 2019 APR was participatory and designed based on statutory requirements and experiences on the part of the technocrats of the Municipality. This is to ensure ownership of the process as well as the outcome.

The preparation of the 2019 APR was coordinated by the Municipal Planning Coordinating Unit (MPCU) which is a statutory body recognized as the planning authority in the Assembly. It is made up of 23 Members including the Heads of the Department of the Assembly, Assembly Members, Representatives of Traditional Authorities among others Members The major steps undertaken to arrive at the completion of the report includes:

1.5.1 Project Inspection and Site Visits

Monthly and other periodic monitoring of projects was carried out through visits to Programme, project and activity sites by the Municipal Monitoring Team made up of members of the Municipal Planning Coordinating Unit (MPCU). The visits enabled the MPCU to assess projects for conformation to specifications, value for money and whether the outputs will help achieve the project objective(s).

These visits also provided the opportunity for the monitoring team to hold sites meetings. These meetings improve accountability as the monitoring team appraised all project/programme and communicated to the relevant actors, communities, departments and institutions of key findings and observations after each project inspection.

1.5.2 Data Collection and Validation

The MPCU collected data on ongoing activities, programmes and projects as well as those implemented from January and December, 2019. The data were reviewed at the meeting of the MPCU and management meeting of the Heads of Department of the Assembly, Unit Heads of the Central Administration and other relevant stakeholders. The Monitoring and Evaluation (M&E) reports prepared were extensively used in the preparation of the 2019 APR. Annual and Quarterly Departmental performance reports submitted by Departments and Institutions in the Assembly provided additional secondary information towards the preparation of this report.

# CHAPTER TWO

# 2.0 MONITORING AND EVALUATION ACTIVITY REPORT

## 2.1 Introduction

The Asante Akim Central Municipal Assembly’s Monitoring and Evaluation Plan for 2019 provides a strategy for the coordinated development of the Municipality in line with the Agenda for Jobs. The Monitoring and Evaluation Plan is a flexible guide to the steps used to document MMTDP activities and how to measure progress towards the achievement of MMTDP goals and objectives in a structured way. This chapter discusses achievements made under the various development dimensions under the agenda for jobs.

Table 2.1 PROJECT REGISTER

| ASANTE AKIM CENTRAL MUNICIPAL ASSEMBLY PROJECT REGISTER - 2019 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SN | PROJECT DESCRIPTION | DEVELOPMENT DIMENSION OF POLICY FRAMEWORK | LOCATION | CONTRACTOR | CONTRACT SUM | SOURCE OF FUDING | DATE OF AWARD | DATE STARTED | EXPECTED DATE OF COMPLETION | EXPENDITURE TO DATE | OUTSTANDING BALANCE | IMPLEMENTATION STATUS (%) | REMARKS |
| 1 | Upgrading of Odumasi Market | Economic Development | Odumasi | Groovies and Tony Limited | 521,892.69 | DACF | 12-Jul-16 | 15-Jul-16 | 15-Feb-17 | 469,563.59 | 52,329.10 | completed |  |
| 2 | Construction of 1 No. 3 Unit Classroom Block and 5 Seater KVIP | Social Development | Kyekyebiase | Nimboat Construction Limited | 236,808.83 | DACF | 23-Apr-18 | 20-Apr-18 | 22-Oct-18 | 207,106.59 | 29,702.24 | completed |  |
| 3 | Construction of Computer Laboratory with Ancillary Facility | Social Development | Praaso | Chrisbel Company Limited | 199,419.85 | DACF | 23-Mar-18 | 20-Apr-18 | 11-Mar-19 | 174,250.35 | 25,169.50 | completed |  |
| 4 | Drilling and mechanization of Borehole | Social Development | Ashiae, Wesley Senior High School and Kyekyewere | MESSR, 88 Integrated Limited | 95,327.00 | DDF | 19-Apr-18 | 26-Apr-18 | 26-Jul-18 | 85,794.30 | 9,532.70 | completed |  |
| 5 | Construction of 1 No. 3Unit Classroom Block with Ancillary Facilities and Mechanized Borehole | social Development | Abosomtweagya | Nimboat Construction Limited | 235,898.63 | DDF | 13-Sep-18 | 29-Sep-18 | 13-Dec-18 | 212,277.28 | 23,621.35 | completed |  |
| 6 | Construction of 1 No. 3 Unit Classroom Block with Ancillary Facilities | social Development | Atunsu | K-Hammer Ventures | 251,981.40 | GET FUND | 15-Mar-19 | 22-Mar-19 | 23-Sep-19 |  | 251,981.40 | On-going |  |
| 7 | Construction of 1 No. 6 Unit Classroom Block with Ancillary Facilities at Konongo Presby 'B' | social Development | Konongo | Agobak Company Limited | 450,797.05 | GET FUND | 15-Mar-19 | 22-Mar-19 | 23-Sep-19 |  | 450,797.05 | On-going |  |
| 8 | Construction of pavilion at Wesley High and St. Mary's High Schools | social Development | Wesley High School and St. Mary's High School | Paa Olu Enterprise | 196,663.00 | DACF | 15-Mar-19 | 22-Mar-19 | 23-Sep-19 | 131,351.40 | 65,311.60 | completed |  |
| 9 | Constgruction of 1 No. 3 Unit Classroom Block with 4-Seater KVIP, Office and Store | social Development | Anawuokrom | Mumed Limited | 218,494.50 | DDF | 30-Apr-19 | 07-May-19 | 07-Nov-19 | 193,855.05 | 24,639.45 | completed |  |
| 10 | Supply and Installation of Transformer for Slaughter House | Economic Development | Konongo-Bomireso | Nimboat Construction works Limited | 52,169.00 | DACF | 14-Nov-18 | 21-Nov-18 | 15-Jan-19 | 52,169.00 | 0.00 | completed |  |
| 11 | Construction of Biogas Digester with Water Treatment Tank at Bomireso Slaughter House | Economic Development | Bomireso | DAS Biogas and Construction Limited | 24,989.00 | DACF | 21-May-19 | 13-Jun-19 | 28-Nov-19 | 22,490.10 | 2,498.90 | completed |  |
| 12 | Reshaping of Selected Roads in Asante Akim Central Municipality | Environment, enfrastructure and human settlement | Municipal Wide | M/S K-Bio | 73,500.00 | DACF | 30-May-19 | 31-May-19 | 14-Jun-19 | 72,044.40 | 1,455.60 | completed |  |
| 13 | Fumigation and Cleaning of Final Works Disposal Site at Bomireso | Environment, enfrastructure and human settlement | Bomireso | Messr Tabi Timbers Company Limited | 48,600.00 | DACF | 03-Jul-19 | 10-Jul-19 | 19-Jul-19 | 48,600.00 | 0.00 | completed |  |
| 14 | Rehabilitation of Rural Technology Facility at Konongo | Economic Development | Konongo - Odumasi | Nuro-Bena Works Company Limited | 38,725.00 |  | 31-May-19 | 14-Jun-19 | 14-Sep-19 | 38,725.00 | 0.00 | completed |  |
| 15 | Construction of Retaining Wall and Filling Works at Bomireso Slaughter House | Economic Development | Bomireso | Adujem Company Limited | 24,963.00 | DACF | 31-Jul-19 | 07-Aug-19 | 09-Sep-19 | 23,739.55 | 1,223.45 | completed |  |
| 16 | Reshaping of 4km Dwease- Boatengkrom Road and 1km Adumkrom Junction to Adumkrom | Environment, enfrastructure and human settlement | Dwease - Boatengkrom and Adumkrom Jtn- Adumkrom | Richgyam Company Limited | 12,500.00 | MP COMMON FUND | 16-Aug-19 | 23-Aug-19 | 06-Sep-19 |  | 12,500.00 | completed |  |
| 17 | Construction of 1 No. 6 Unit Classroom Block with Library, Store and Office at Anuruso | social Development | Anuroso | Mssrs Nimboat Construction Works | 455,633.40 | GET FUND | 10-Jul-19 | 17-Jul-19 | 17-Jan-20 |  | 455,633.40 |  |  |
| 18 | Construction of 1 No. 6 Unit Classroom Block with Library, Store and Office at Konongo MA | social Development | Konongo | Naska Services Limited | 449,339.11 | GET FUND | 10-Jul-19 | 17-Jul-19 | 17-Jan-20 |  | 449,339.11 |  |  |
| 19 | Supply of 300 No. Mono Desks and 200 No. Dual Desks for Schools in the Municipality | social Development | Municipal Wide | S. K. Ayensu Ventures | 79,500.00 | DACF | 27-Aug-19 | 03-Sep-19 | 28-Oct-19 | 79,500.00 | 0.00 | completed |  |
| 20 | construction 1No. 5 Unit KG and lower primary classroom block with ancillary facility, 5 seater squat w/c toilet with mechanized bore and over tank and supply of school furniture at Kyekyewere | social Development | Kyekyewere | HAJIA RUKAYA BONAH ENTERPRISE | 436,122.00 | DDF | 15-Oct-19 |  |  | 65,418.30 | 370,703.70 | On-going |  |
| 21 | Supply of Complete sets of streetlights for the municipality | social Development | Municipal Wide | Stanok Enterprise | 43,260.00 | MP COMMON FUND | 19-Aug-19 | 20-Aug-19 | 27-Aug-19 |  | 43,260.00 | completed |  |
| 22 | supply of 60 complete set of streetlights | social Development | Municipal Wide | stanok enterprise | 43,260.00 | DACF | 19-Aug-19 |  |  |  | 43,260.00 |  |  |
| 23 | Clearing and evacuation of two dump sites | Environment, infrastructure and human settlement | Odumasi | Tabi Timbers and Company Limited | 37,400.00 | DACF | 08-Oct-19 | 11-Oct-19 | 25-Oct-19 | 0.00 | 37,400.00 | completed |  |

Table 2.2: OTHER PROJECTS

The table below illustrates other on-going projects in the Municipality implemented by the Central government.

| ASANTE AKIM CENTRAL MUNICIPAL ASSEMBLY IPEP PROJECT REGISTER-2019 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SN | PROJECT DESCRIPTION | DEVELOPMENT DIMENSION OF POLICY FRAMEWORK | LOCATION | CONTRACTOR | CONTRACT SUM | SOURCE OF FUDING | DATE OF AWARD | DATE STARTED | EXPECTED DATE OF COMPLETION | EXPENDITURE TO DATE | OUTSTANDING BALANCE | IMPLEMENTATION STATUS (%) | REMARKS |
| 1 | Construction of 1 No. Community-based Solar Power Water System | Social Development | Odumasi New Town | NA | NA | GOG | NA | NA | NA | NA | NA | NA | On-going |
| 2 | Construction of 1 No. Community-based Solar Power Water System | Social Development | Abosomtweagya | NA | NA | GOG | NA | NA | NA | NA | NA | NA | On-going |
| 3 | Construction of 1 No. Community-based Solar Power Water System | Social Development | Patriensa | NA | NA | GOG | NA | NA | NA | NA | NA | NA | On-going |
| 4 | Construction of 1 No. 10-Seater Water Closet Institutional Toilets with Mechanized boreholes | Social Development | Nyaboo | NA | NA | GOG | NA | NA | NA | NA | NA | NA | On-going |
| 5 | Construction of 1 No. 10-Seater Water Closet Institutional Toilets with Mechanized boreholes | Social Development | Dwease, | NA | NA | GOG | NA | NA | NA | NA | NA | NA | On-going |
| 6 | Construction of 1 No. 10-Seater Water Closet Institutional Toilets with Mechanized boreholes | Social Development | Kyekyebiase | NA | NA | GOG | NA | NA | NA | NA | NA | NA | On-going |
| 7 | Construction of 1 No. 10-Seater Water Closet Institutional Toilets with Mechanized boreholes | Social Development | Obenemase | NA | NA | GOG | NA | NA | NA | NA | NA | NA | On-going |
| 8 | Construction of 3 Unit Classroom Block at with Ancillary Facilities | Social Development | Adumkrom | NA | NA | GOG | NA | NA | NA | NA | NA | NA | On-going |
| 9 | Construction of 3 Unit Classroom Block with Ancillary Facilities | Social Development | Boatengkrom | NA | NA | GOG | NA | NA | NA | NA | NA | NA | On-going |
| GHANA FIRST PROJECT REGISTER-2019 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Construction of 1 No. 20 Seater Type B Toilet Facility | Social Development | Konongo Ahenbronum | TUNSUMA CONSTRUCTION LIMITED | 333,676.00 | GOG | 30-Aug-18 | NA | NA | NA | NA | NA | On-going |
| 2 | Construction of 1 No. 20 Seater Type B Toilet Facility | Social Development | Odumase Zongo | TUNSUMA CONSTRUCTION LIMITED | 333,676.00 | GOG | 30-Aug-18 | NA | NA | NA | NA | NA | On-going |
| 3 | Construction of 1 No. 20 Seater Toilet Facility | Social Development | Odumase Apebourso | TUNSUMA CONSTRUCTION LIMITED | 503,935.08 | GOG | 30-Aug-18 | NA | NA | NA | NA | NA | On-going |
| 4 | Construction of 1 No. 14 Seater Toilet Facility | Social Development | Konongo Ward 6 | TUNSUMA CONSTRUCTION LIMITED | 871,452.81 | GOG | 30-Aug-18 | NA | NA | NA | NA | NA | On-going |
| 5 | Construction of 1 No. 14 Seater Toilet Facility | Social Development | Praaso Salaam |  |  | GOG | 30-Aug-18 | NA | NA | NA | NA | NA | On-going |
| 6 | Construction of 1 No. 14 Seater Toilet Facility | Social Development | Obenemase |  |  | GOG | 30-Aug-18 | NA | NA | NA | NA | NA | On-going |
| 7 | Construction of 1 No. 14 Seater Toilet Facility | Social Development | Kyekyebiase | TUNSUMA CONSTRUCTION LIMITED | 290,484.27 | GOG | 30-Aug-18 | NA | NA | NA | NA | NA | On-going |
| 8 | Construction of 1 No. 20 Seater Toilet Facility | Social Development | Dwease- Ahenbronum | TUNSUMA CONSTRUCTION LIMITED | 503,935.08 | GOG | 30-Aug-18 | NA | NA | NA | NA | NA | On-going |

NB: NA- not available

The tables below represent the proportion of the DMTDP implemented in 2019 as against 2018. In 2019, out of the Forty-Eight (48) projects, Seventy- six percent (76) were successfully completed whiles 8.7% are still on-going. Table 2.3 and 2.4 describe a detail status of the DMTDP

Table 2.3 Proportion of the DMTDP Implemented in 2019

| Indicators | Baseline 2017 | 2018 |  | 2019 |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Target | Actual | Target | Actual |
| Proportion of the annual action plan implemented |  |  |  |  |  |
| - Percentage completed | 57 | 100 | 70 | 100 | 78 |
| - Percentage of ongoing interventions | 39 | - | 10 | - | 9 |
| - Percentage of interventions abandoned | - | - | - | - | - |
| - Percentage of interventions yet to start | 4 | 0 | 20 | - | 13 |
| - Percentage of interventions executed outside plan | - | - | - | - | 0.00 |
| - Proportion of the overall medium-term development plan implemented | - | 20.3 | 17.1 | 34 | 32.5 |

MPCU, AACMA, (January, 2020)

Table 2.4 Details of the Annual Action Plan Implemented

| S/N | Development Dimension | 2017 |  | 2018 |  | 2019 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Plan | Exec | Plan | Exec | Plan | Exec |
| 1 | Economic Development | 7 | 3 | 8 | 6 | 8 | 6 |
| 2 | Social development | 16 | 12 | 14 | 11 | 27 | 25 |
| 3 | Environment, Infrastructure And Human Developments | 12 | 8 | 4 | 2 | 5 | 5 |
| 4 | Governance, Corruption And Public Accountability | 12 | 9 | 14 | 12 | 8 | 6 |
| Total |  | 47 | 32 | 40 | 31 | 48 | 42 |

MPCU, AACMA, (January, 2020)

2.2 ASSESSMENT OF PERFORMANCE INDICATORS

2.3 Agricultural

Agricultural is the main stay of the Municipal economy and is the major source of food, employment and income for most of the population in the Municipality. This section of the report present crops out-puts of the year under review.

From the table below, the total output of crop yield for the year under review is 74,478.37 as against the targeted output of 69,935.38. This represent over 106 % of the expected output. The table below

|  | Indicator (categorized by development Dimension of Agenda for jobs) |  | Baseline |  | 2018 |  | 2019 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | ECONOMIC DEVELOPMENT |  | 2017 |  | Target | Actual | Target | Actual |
| 1 | Total output in agricultural production |  |  |  |  |  |  |  |
|  | - Maize |  | 367.2 |  | 403.92 | 489.2 | 557.4 | 506.7 |
|  | - Rice (milled) |  | 408.1 |  | 448.91 | 454.3 | 483.6 | 641.9 |
|  | - Cassava |  | 9,374.8 |  | 10,312.3 | 8,656 | 9,694 | 9,181.20 |
|  | - Yam |  | 358.5 |  | 394.35 | 400.38 | 440.38 | 416.37 |
|  | - Cocoyam |  | 1,915.9 |  | 2,107.5 | 1,690 | 1,859 | 1,799.90 |
|  | - Plantain |  | 5,819 |  | 6,400.9 | 5,452 | 7,087 | 7,400.30 |
|  | - Cocoa |  | - |  | - | 10,028.63 | - | - |
|  | - Cattle |  | 617 |  | 647 | 673 | 740 | 713 |
|  | - Sheep |  | 4,952 |  | 5,348 | 5,722 | 6,580 | 6,179 |
|  | - Goat |  | 5,629 |  | 6,023 | 6,384 | 7, 788 | 7,277 |
|  | - Pig |  | 1,693 |  | 1,778 | 1,858 | 2,006 | 1,988 |
|  | - Poultry |  | 29,364 |  | 32,300 | 35,207 | 40,488 | 38,375 |
|  | Total |  | 60,498.50 |  | 66,163.88 | 77,014.51 | 69,935.38 | 74,478.37 |
| 2 | Percentage of arable land under cultivation (Hecters) |  | - |  |  | 10,045.00 | 10,597.48 | 10,597.48 |
| AACMA, MOFA, (January, 2020) Table 2:5 Employment by Sector |  |  |  |  |  |  |  |  |
| 3 | Number of new industries established |  | 2017 Baseline |  | 2018 |  | 2019 |  |
|  |  |  |  |  | Target | Actual | Target | Actual |
|  | - Agriculture |  | - |  | - | - |  |  |
|  | - Industry |  | - |  | - | - |  |  |
|  | - Service |  | - |  | - | - |  |  |
| 4 | Number of new jobs created |  |  |  |  |  |  |  |
|  | - Agriculture |  |  |  |  | 31 |  |  |
|  | - Industry |  |  |  |  | 21 |  |  |
|  | - Service |  | - |  | - | 340 |  |  |
| GSS, DAR, (January, 2020) - SOCIAL DEVELOPMENT - Education Education is essential for the development of the requisite human resource needed accelerated socio-economic development. In other to track progress on the educational performance in the Municipality, certain indicators such as Net enrolment ratio, Gender parity index and Completion rate are measured. In 2019, the net enrollment rate recorded for KG, Primary and JHS are 71.90%, 99.80% and 52.10% respectively. Table 2.6 represent the performance of educational indicators for the year under review Table2.6 Educational Parameters |  |  |  |  |  |  |  |  |
| 5 | Net enrolment ratio |  | 2017 Baseline |  | 2018 |  | 2019 |  |
|  |  |  |  |  | Target | Actual | Target | Actual |
|  | Kindergarten |  | 76.5% |  | 90 | 82.5 | 72.1% | 71.90% |
|  | Primary |  | 102.9% |  | 115 | 103.0 | 102.0% | 99.80% |
|  | JHS |  | 53.9% |  | 55 | 56.8 | 51.1% | 52.10% |
|  | SHS |  | 61.1% |  | 70 | 68.3 | - | - |
| 6 | Gender parity index |  |  |  |  |  |  |  |
|  | Kindergarten |  | 1.05 |  | 110 | 1.03 | 0.98 | 97.50% |
|  | Primary |  | 1.13 |  | 115 | 1.12 | 1.08 | 1.05 |
|  | JHS |  | 1.00 |  | 1.00 | 1.02 | 1.02 | 1.01 |
|  | SHS |  |  |  |  | - | 1.14 | 1.11 |
| 7 | Completion rate |  |  |  |  |  |  |  |
|  | Kindergarten |  | 116.2% |  | 117 | 113.8 | - | - |
|  | Primary |  | 115.7% |  | 117 | 113.5 | 106.9% | 103.7% |
|  | JHS |  | 78.7% |  | 80 | 85.4 | 79.7% | 81.15 |
|  | SHS |  | 91.9% |  | 100 | 116.7 | - | - |
| Source: GES, AACMA, (January, 2020) - Health The overall health condition of every society is very critical to its development. Good health condition empowers the working population and thereby increase productivity. The table below represent the recorded health indicators for 2019 as against 2017 Form the table below, the total number of health facilities increased from 12 to 15 from 2017 to 2019 respectively. Table 2.7 Health |  |  |  |  |  |  |  |  |
|  |  |  | 2017 |  | 2018 |  | 2019 |  |
| 8 | Number of operational health facilities |  | Public | Private | Public | Private | Private | Public |
|  | CHPS Compound |  | 4 | - | 6 | 5 | 5 | - |
|  | Clinic |  | - | 2 | - | - | 3 | 1 |
|  | Health center |  | 3 | - | 3 | 3 | - | 4 |
|  | Hospital |  | 1 | 2 | - | 1 | 1 | 1 |
|  | Maternal mortality ratio (institutional) |  | 0/100,000 |  |  |  | 0 | 0 |
|  | Malaria case fatality (institutional) |  |  |  |  |  | 0 | 0 |
|  | - Sex |  |  |  |  |  | 0 | 0 |
|  | - Age group |  |  |  |  |  | 0 | 0 |
| 9 | Proportion of population with valid NHIS card |  |  |  |  |  |  |  |
|  | Total (by sex) | Male | 25,248 |  | 32,028.00 | 21,372.00 | 26,974 | 27,956 |
|  |  | Female | 38,010 |  | 46,095.00 | 32,837.00 | 40,461 | 40,366 |
|  |  | Total | 63,258 |  | 78,123.00 | 54,209.00 | 67,435 | 68,322 |
|  | - Indigents |  | 1879 |  | 3371 | 91 | 113 | 678 |
|  | - informal |  | 21067 |  | 26163 | 18916 | 23,445 | 25394 |
|  | - Aged |  | 3383 |  | 3738 | 2889 | 3,581 | 3,342 |
|  | - Under 18 years |  | 29153 |  | 33638 | 25752 | 31,917 | 32,372 |
|  | - Pregnant women |  | 4257 |  | 7475 | 3378 | 4,187 | 3,096 |
|  | - SSNIT Contributors |  | 3372 |  | 3588 | 3158 | 3,914 | 2,955 |
|  | - SSNIT Pensioners |  | 147 |  | 150 | 225 | 278 | 485 |
|  | Total |  | 63,258 |  | 78,123 | 54,409 | 67,435 | 68,322 |

NHIS, AACMA, (February, 2020)

Note: *the above information covers both Asante Akim North District Assembly and Asante Akim Central Municipal Assembly

The table below outlines information on the registration of birth and deaths. A total number of 3295 births were registered whereas 177 deaths were recorded in 2019.

Table 2.8.  Birth and Death Register

|  | Indicator (Categorized by Development Dimension of Agenda for jobs) |  |  | Baseline | 2017 | Actual 2018 | 2019 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | Target | Actual |
| 10 | Number of births and deaths registered |  |  |  |  |  |  |  |
|  | - Birth (sex) |  | Male | 1339 | 1200 | 1353 | 4000 | 1801 |
|  |  |  | Female | 1161 | 1000 | 1213 |  | 1494 |
|  | - Death |  | Male | 106 | 100 | 94 | 300 | 101 |
|  |  |  | Female | 65 | 60 | 82 |  | 76 |
| AACMA, Birth and Death Registry, (January, 2019) 2.4.4 Access to Safe Drinking Water Sources The Availability and accessibility to safe drinking water is an important aspect of the health of the population. The provision of safe and accessible water source to the inhabitant has been a challenge to the Assembly. Table 2.9 represent the proportion and percentage of the population with access to safe water source. Form the table, the percentage of rural population with access to safe drinking water source increase from 57% to 69% from 2017 to 2018. Below is the detailed presentation of the percentage and proportion of population with access to safe drinking water sources. Table 2.9 Access To Safe Drinking Water Sources |  |  |  |  |  |  |  |  |
| 11 | Percent of population with access to safe drinking water sources |  |  | 2017 Baseline | 2018 Target | 2018 Actual | 2019 Target | 2019 Actual |
|  | District |  |  | 63.1 | 69.4 | 76.3 | 83 | 81 |
|  | Urban |  |  | 68.7 | 75.6 | 83.1 | 86 | 83 |
|  | Rural |  |  | 57.4 | 63.1 | 69.5 | 80 | 79 |
| 12 | Proportion of population with access to safe drinking water source |  |  |  |  |  |  |  |
|  | District |  |  | 68,120 | 80,000 | 71,337 | 80,000 | 64,800.00 |
|  | Urban |  |  | 57,575 | 65,000 | 59,006 | - | 39,342.00 |
|  | Rural |  |  | 10,545 | 15,000 | 12,331 | - | 25,458.00 |
| There were no recorded cases of child trafficking in the year 2019. However, there was an increase case of child abuse from 8 (2018) to 9 (2019) among females whiles that of the male case reduced from 12 (2018) to 11 (2019). The Table below illustrate recorded cases of child trafficking and abuse by Sex. Table 2.10 Child Trafficking and Abuse |  |  |  |  |  |  |  |  |
| 15 | Number of recorded cases of child trafficking and abuse |  |  | 2017 Baseline | 2018 Target | 2018 Actual | 2019 Target | 2019 Actual |
|  | Child trafficking (sex) | Male |  | - | - | - | - | - |
|  |  | Female |  | - | - | - | - | - |
|  | Child abuse (sex) | Male |  | 8 | - | 12 |  | 11 |
|  |  | Female |  | 6 | - | 8 |  | 9 |
| In the table below, Ninety- Eight percent (98%) of communities in the Municipality are covered with electricity. In terms of crime cases, a total of 2079 were reported. |  |  |  |  |  |  |  |  |
| 16 | Percentage of road network in good condition |  |  | 2017 Baseline | 2018 Target | 2018 Actual | 2019 Target | 2019 Actual |
|  | - Total |  |  | 45 | 50 | 48 | 45 |  |
|  | - Urban |  |  | 55 | 60 | 58 | 40 | 25 |
|  | - Feeder |  |  | 35 | 50 | 38 | 50 | 40 |
| 17 | Percentage of Communities covered by electricity |  |  |  |  |  |  |  |
|  | - District |  |  | 89.5 | 92.5 | 90 | 94 | 93 |
|  | - Rural |  |  | 82 | 85 | 82 | 87 | 84 |
|  | - Urban |  |  | 97 | 100 | 98 | 100 | 98 |
| 18 | Reported cases of crime |  |  |  |  |  |  |  |
|  | - Men |  |  | 973 | - | 1,077.00 |  | 2079 |
|  | - Women |  |  | 472 | - | 528 |  |  |
|  | - Children |  |  | 98 | - | 112 |  |  |
| NB: The date for reported crime cases was not sex disaggregated 2.4.5 Disaster Occurrence The table below shows the disaster occurrence for the year under review. From the table, it can be said there were no recorded case of bushfire but there were 51 occurrence of flood. Table 2.11 Disaster Occurrence |  |  |  |  |  |  |  |  |
| 20 | Number of communities affected by disaster |  |  | 2017 Baseline | 2018 Target | 2018 Actual | 2019 Target | 2019 Actual |
|  | - Bush fire |  |  | 0 | - | 1 | 5 | - |
|  | - Floods |  |  | 0 | - | 1 | 3 | 2 |
|  | - Rainstorm |  |  | 1 | - | 26 | 5 | 4 |

NADMO, AACMA, (January, 2020)

Update on Revenue Source and Disbursement

The table below shows the revenue and expenditure for the assembly for the year under review. Out of all the sources of revenue, DACF recorded the highest contribution of 1,851,477.92, IGF contribution was 1,087,566.22 with the lowest contribution of 12,681.98 coming from MSHAP. Also, the total compensation and goods and services were 270,982.29 and 658,858.48. This is represented in the table below.

| EXPENDITURE ITEM | Baseline 2017 | Budget 2018 | Actual 2018 | Budget 2019 | Actual 2019 |
| --- | --- | --- | --- | --- | --- |
| IGF |  | 1,292,930.00 | 863,659.84 | 1420,490.21 | 1,087,566.22 |
| DACF |  | 3190,849.51 | 1,482,873.11 | 3,789,668.65 | 1,851,477.92 |
| MP’s CF |  | 400,000.00 | 412,515.14 | 750,000.00 | 359,907.78 |
| PWDs CF |  | 493,728.92 | 228,516.80 | 113,689.75 | 164,151.44 |
| MSHAP |  |  |  | 12,681.98 | 12,681.98 |
| MAG |  |  |  | 172,948.68 | 172,376.11 |
| DDF |  | 936,416.00 | 422,633.00 | 570,219.00 | 311,130.27 |
| DPAT |  |  |  | 4666,000.00 | 465,678.00 |
| UDG |  | 341,000.00 |  |  |  |
| TOTAL |  | 1,277,416.00 | 422,633.00 | 5,236,219.00 | 776,808.27 |

Finance Dept, AACMA, (January, 2020)

Table 2.12 Update on Revenue Source and Disbursement.

| EXPENDITURE ITEM | Baseline 2017 | Budget 2018 | Actual 2018 | Budget 2019 | Actual 2019 |
| --- | --- | --- | --- | --- | --- |
| Compensation | 2292094 | 139,887.00 | 107,538.47 | 296,020.00 | 270,982.29 |
| Goods And Service | 2851957 | 2,723,545.00 | 1,739,437.96 | 862,190.21 | 658,858.48 |
| Others | 3,959,983 | 469,207.00 | 241,001.32 | 42,004.00 | 34,9781.61 |
| TOTAL | 9,104,034 | 3,332,639.00 | 2,087,977.75 | 1,200,214.21 | 1,279,622.38 |

Finance Dept, AACMA, (January, 2020)

Table 2.18: Critical Development and Poverty Issues

|  | 2019 |  |  |  |
| --- | --- | --- | --- | --- |
| Critical Development and Poverty Issues | Allocation GH¢ | Actual receipt GH¢ | No of beneficiaries |  |
|  |  |  | Targets | Actuals |
| Ghana School Feeding Programme | - |  |  | - |
| Capitation Grants | 161285.1 | 161,285.1 | 15,900 | 15,900 |
| National Health Insurance Scheme | - |  |  |  |
| Livelihood Empowerment Against Poverty (LEAP) programme | - |  |  | - |
| National Youth Employment Program | - | - | - | - |
| One District-One Factory Programme | - | - | - | - |
| One Constituency-One Million Dollars Programme | N.A | N.A | N.A | N.A |
| Planting for Food and Jobs Programme | 45,353.23 | 25,800 | 3,000 | 2,856 |
| Planting for Export and Rural Development | 17,800 | 1,180 | 1,000 | 675 |
| Free SHS Programme | - | - | - | - |
| National Entrepreneurship and Innovation Plan (NEIP) | - | - | - | - |
| Implementation of Infrastructural for Poverty Eradication Programme (IPEP) | N.A | N.A | N.A | N.A |

MPCU, AACMA, (January, 2019)

Note: *The information on school feeding does not cover the whole the 2018/19 academic year.

# CHAPTER THREE

# RECOMMENDATIONS AND CONCLUSION

## 3.1 RECOMMENDATIONS ON THE VARIOUS GOALS

Build a Prosperous Society

- Improve the Assembly’s internally generated revenue to complement the effort of Central Government funding sources for development

- Improve Assembly’s expenditure management

- The involvement of the private sector in revenue mobilization

- Improve internal financial management measures to minimize the leakages and waste

Create Opportunity for All

- Support the private sectors in the municipality to sustain continuous production especially those in the informal sector of the local economy.

- Facilitate the development of employable skills among the youth by supporting the technical and vocational schools in the Municipality.

- Increase farmers access to credit facilities and technical support.

- Promote both traditional and non-traditional crops production and vegetable farming

Safeguard the Natural Environment and Ensure a Resilient Built Environment

- Organize training workshops for farmers on new technologies of farming

- Regular preparation and updating of settlement planning schemes

- Conduct periodic socio-economic survey on population and development.

- NADMO should be resource to embark on regular public education on disaster preventive measure

Maintain a Stable, United and Safe Society

- Embarking on a capacity building programme to ensure the proper functioning of all the sub-structures and units of the Assembly

- Sensitize the people on the importance of the local government system and their roles to contributing to decentralized accountable governance

- Encourage the participation of citizens in community developmental issues

- Organize periodic seminars, workshops, job-training for the Assembly members

### 3.2 Conclusion

The report cover activity forms the various department and unit in the municipality. It also identifies problems/challenges and has made recommendations to help tackle these myriad of problems in the Municipality. It is hoped that these recommendations would be well considered and pursued to ensure that the living conditions of the people in the Municipality is ultimately improved

The Assembly, will continue to laisse with other stakeholders including decentralized departments, Non-Governmental Organizations (NGOs) and the Private Sector, to ensure effectiveness in the mobilization and utilization of resources in the provision basic social and economic infrastructure and services in the municipality, as relevant to achieving the set goals of the Ghana Shared Growth and Development Agenda (GSGDA) in the Asante Akim Central Municipality.